## Master Tracker
Street Vendor Site Selection Tool — Data Acquisition Tracker (OFFICIAL)
Live XYZ × NYC SBS (Office of Street Vendor Services) × Street Vendor Project ¦ v2.0 — rebuilt 2026-06-03 ¦ Supersedes Phase 1 inventory v1.0 (May 2026)
Verification column reflects independent link/source checks performed 2026-06-03. "Owner" and dates carried from v1.0 inventory. P1 rows shaded red = blocking for rule encoding.
ID | Source agency | Dataset / layer | Type | Format | Access status | Priority | Blocks deliverable | Update cadence | Purpose / what it drives | Direct URL | Verification (2026-06-03) | Acquisition notes & risks | Owner | Target date | Status
DS-001 | DOHMH | Mobile Food Vending Restricted Streets — GIS layer | Rule polygon | Internal GIS (Esri) | Request to agency | P1 | D3 (rule library, MFV legal surface) | Ad-hoc / amended | Canonical food-vendor no-go segments with hours/days. Single most important rule input. | open ↗ | Public map confirmed; GIS layer NOT yet requested | Public artifact is PDF only. Internal GIS is what powers the agency's interactive map. Fallback is PDF geocoding (~2 eng-weeks). ¦ Public interactive map live at a816-dohbesp.nyc.gov/IndicatorPublic/mobilefoodvending. Underlying GIS export still requires agency request. | Live XYZ — Data Lead | 2026-06-21 | Not started
DS-002 | DOHMH | Mobile Food Vending Restricted Streets Guide (PDF) | Rule polygon (fallback) | PDF | Public | P2 | D3 fallback | Ad-hoc | Tabular borough-by-borough fallback if DS-001 not provided. Geocode against CSCL. | open ↗ | Verified live (2026-06-03) | Borough sections, named zones (WTC, Flushing, Dyker Heights). ¦ DOHMH MFV Restricted Streets PDF link confirmed reachable. | Live XYZ — Data Lead | 2026-06-08 | Not started
DS-003 | DOHMH | Restricted Area Permit zones | Rule polygon | Internal | Request to agency | P1 | D3 (Restricted Area SKU) | Ad-hoc | Defines the specific high-traffic zones requiring Restricted Area Permit (separate SKU). | open ↗ | Unverified — from internal inventory | May be administrative boundaries, not formal GIS. Confirm with DOHMH permitting. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-06-28 | Not started
DS-004 | DOHMH | Mobile Food Vendor permits (active holders) | Permit population | CSV / API | Public via NYC Open Data | P2 | — | Weekly | Calibration of legal-surface against where permits actually operate; informs heatmap. | open ↗ | Public source — link present in inventory | Public dataset. Cross-reference for evaluation §IV.4.b. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-14 | Not started
DS-005 | DOHMH | Green Cart designated under-served neighborhood polygons | Rule polygon | Internal | Request to agency | P1 | D3 (Green Cart mode) | Annual | Green Cart MFV permits limited to specific Police Precinct geographies in lower-income areas. | open ↗ | Unverified — from internal inventory | Boundaries set by Local Law 9 of 2008. May exist as a published list of precincts requiring conversion to GIS. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-06-21 | Not started
DS-006 | DOHMH | Hospital facilities (DOHMH-licensed) | Buffer anchor | GeoJSON / CSV | Public via NYC Open Data | P2 | — | Quarterly | Anchor for hospital-adjacency no-vending rule §20-465(b)(v). | open ↗ | Public source — link present in inventory | Cross-check against DCP FacDB factype 3102 for completeness. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-21 | Not started
DS-007 | DCWP | General Vendor Street Restrictions — Esri feature service | Rule polygon | ArcGIS REST / GeoJSON | Public via ArcGIS Experience; license preferred | P1 | D3 (GV legal surface) | Ad-hoc | Authoritative DCWP-administered street restrictions for general (merchandise) vendors per §20-465 / §20-465.1. | open ↗ | Verified live (2026-06-03) | Underlying feature service is reachable but written license is the responsible path before production use. ¦ DCWP ArcGIS Experience confirmed live via DSNY enforcement page. This IS the public General Vendor Street Restrictions Map. | Live XYZ — Data Lead | 2026-06-21 | Not started
DS-008 | DCWP | Street Vendor Review Panel (SVRP) designations under §20-465.1 | Rule polygon | Internal / SBS records | Request to agency | P2 | — | Ad-hoc | Streets added/removed from the general-vendor permitted set by SBS designation since 1995. | open ↗ | Unverified — from internal inventory | May overlap with DS-007. SBS is the actual record holder (the panel chair is the SBS Commissioner's designee). ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-07-05 | Not started
DS-009 | DCWP | General Vendor License records (active holders) | Permit population | CSV / API | Public via NYC Open Data | P2 | — | Quarterly | Active general vendor license population — feeds the cap-tracking and post-Int. 431-B expansion modeling. | open ↗ | Public source — link present in inventory | Verify SKU breakdown (general vs. Yellow vs. Blue) in column schema. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-21 | Not started
DS-010 | DCWP | Specialized Vending License records (Yellow + Blue) | Permit population | Internal | Request to agency | P2 | — | Quarterly | Splits Yellow (Citywide Specialized) vs. Blue (Midtown Core) populations; underpins SKU-specific map mode. | open ↗ | Unverified — from internal inventory | Sensitive PII; only aggregate counts and license-type breakdown needed for the tool. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-07-05 | Not started
DS-011 | DCWP | Midtown Core (Blue) Specialized waiting-list metadata | Permit population | Internal | Request to agency | P3 | — | Ad-hoc | Informational only — not encoded in rule logic but provides context for vendor outreach prioritization. | open ↗ | Unverified — from internal inventory | Likely just aggregate counts. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-07-19 | Not started
DS-012 | DCP | NYC GIS Zoning Features | Rule polygon | Shp / GeoJSON | Public | P1 | D3 (C4/C5/C6 exclusion) | Quarterly | Drives the §20-465 C4/C5/C6 general-vendor zoning-district exclusion. Critical for SKU-specific legality. | open ↗ | Public source — link present in inventory | Filter ZONEDIST starts-with C4/C5/C6; dissolve to single exclusion polygon. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-07 | Not started
DS-013 | DCP | NYC Street Centerline (CSCL) | Base geography | Shp / GeoJSON | Public | P1 | D3 (base join key — ALL rules) | Daily | Primary streets layer; segment IDs are the join key for DOHMH/DCWP street-level restrictions. | open ↗ | Public source — link present in inventory | Daily refresh — design ingest job accordingly. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-07 | Not started
DS-014 | DCP | LION Street Network | Base geography | Shp / FGDB | Public | P2 | — | Quarterly | Fine-grained segmentation; needed where DOHMH restrictions describe partial blocks ('from X to Y'). | open ↗ | Unverified — from internal inventory | Use in tandem with CSCL — LION for partial-block resolution, CSCL for production segment IDs. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-06-14 | Not started
DS-015 | DCP | Building Footprints | Base geography + buffer anchor | Shp / GeoJSON | Public | P2 | — | Daily | Anchor for the 20-ft entrance/exit buffer. Door-level data not included — approximation only. | open ↗ | Public source — link present in inventory | 20-ft buffer from footprint edge is an over-approximation of the rule (which targets entrances). Accept for v1. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-14 | Not started
DS-016 | DCP | MapPLUTO | Base geography | Shp / CSV | Public | P3 | — | Quarterly | Parcel-level zoning lookup; supplemental to DS-012. Useful for parcel-aware UX (storefront context). | open ↗ | Unverified — from internal inventory | Live XYZ already uses MapPLUTO for storefront index — license is in place. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-06-21 | Not started
DS-017 | DCP | Facilities Database (FacDB) — Shapefile | Buffer anchor | Shp | Public | P2 | — | Annual | Hospitals (factype 3102), schools (factype 5xxx) in one consolidated layer. | open ↗ | Public source — link present in inventory | Annual refresh — verify currency against agency-specific datasets. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-14 | Not started
DS-018 | DCP | Borough Boundaries | Base geography | Shp / GeoJSON | Public | P3 | — | Annual | Frame layer for borough-specific MFV permits (SKU separation). | open ↗ | Public source — link present in inventory | Trivial ingest. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-07 | Not started
DS-019 | DCP | Community Districts | Advisory / context | Shp | Public | P3 | — | Ad-hoc | Reporting and outreach segmentation. | open ↗ | Public source — link present in inventory | Used for metrics dashboard segmentation only. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-07-12 | Not started
DS-020 | SBS | Street Vendor Review Panel — designation history | Rule polygon supplement | Internal | Request to agency | P2 | — | Ad-hoc | SBS-administered §20-465.1 designations adding/removing streets from the permitted set. | open ↗ | Unverified — from internal inventory | May be redundant with DS-008. Confirm canonical source with SBS Legal. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Project Lead | 2026-06-21 | Not started
DS-021 | SBS | Business Improvement District (BID) boundaries | Advisory / context | Shp / GeoJSON | Public | P3 | — | Annual | Informational overlay; some BIDs administer supplementary vending arrangements. | open ↗ | Public source — link present in inventory | Useful for outreach targeting and brick-and-mortar context. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-21 | Not started
DS-022 | SBS | BID Directory (contacts, programming) | Advisory / context | CSV / API | Public via NYC Open Data | P3 | — | Quarterly | Contact metadata for the BIDs in DS-021; informs Phase 3 outreach. | open ↗ | Public source — link present in inventory | — ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Project Lead | 2026-07-12 | Not started
DS-023 | DSNY | ECB vendor citation records (geocoded) | Operational / measurement | Internal | Request to agency / OpenRecords | P1 | D2/D4 evaluation metrics | Monthly | Citation locations, code sections, dispositions. Underpins §IV.4.a evaluation and 75%-overturn root-cause analysis. | open ↗ | Unverified — from internal inventory | Some summary data on OATH (ECB) public records. Granularity is the issue. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-06-28 | Not started
DS-024 | DSNY | Enforcement zone / patrol allocation | Operational / advisory | Internal | Request to agency | P3 | — | Ad-hoc | Context only — where DSNY focuses enforcement; informs metric interpretation. |  | Unverified — from internal inventory | Likely sensitive; may not be released externally. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Project Lead | 2026-07-19 | Not started
DS-025 | NYPD | Vendor-related summons records | Operational / measurement | Internal / FOIL | Partial public via NYPD Open Data | P2 | — | Monthly | Pre-March 2026 criminal summons history; post-LL122 will shift to ECB. | open ↗ | Unverified — from internal inventory | Granularity often only aggregate. Pursue via FOIL if NYPD Legal route stalls. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Project Lead | 2026-07-05 | Not started
DS-026 | DOT | Pedestrian Plazas (Polygon) | Out-of-scope mask | Shp / GeoJSON | Public | P2 | — | Annual | Mask plaza surfaces from the legal-vending canvas; vending in plazas is concession-only and out of scope. | open ↗ | Public source — link present in inventory | Surface as 'out of scope' in the UX, not as 'prohibited'. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-14 | Not started
DS-027 | DOT | Bus Stop Shelters | Buffer anchor | Shp / GeoJSON | Public | P2 | — | Quarterly | Anchors the no-vending-at-bus-stops rule. | open ↗ | Public source — link present in inventory | Cross-reference with MTA Bus Stops (DS-035) for completeness. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-14 | Not started
DS-028 | DOT | No-Standing / No-Parking signs | Buffer anchor | Shp / CSV | Public | P2 | — | Monthly | Filter for hospital-adjacency no-standing zones — underpins §20-465(b)(v). | open ↗ | Public source — link present in inventory | Sign-by-sign data — needs spatial join to hospitals to derive the no-vending polygon. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-28 | Not started
DS-029 | DOT | Curb-cut / Driveway inventory | Buffer anchor | Uncertain | Gap / request to agency | P2 | — | Uncertain | 10-ft driveway-buffer rule. No clean citywide layer found in public open data. | open ↗ | Unverified — from internal inventory | Likely partial coverage in DOT records; fallback is OSM/building-footprint derivation. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-07-05 | Not started
DS-030 | DOT | DOT Sidewalk Inventory (if available) | Base geography | Internal | Request to agency | P3 | — | Ad-hoc | Production-grade sidewalk polygons would replace the community Sidewalk Widths NYC dataset. | open ↗ | Unverified — from internal inventory | May be in progress at DOT. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Project Lead | 2026-07-19 | Not started
DS-031 | DOT | Crosswalks (derived from CSCL intersection nodes) | Buffer anchor | Derived | Derived in-house | P2 | — | Daily | 10-ft crosswalk buffer per §20-465(b)(iv). | open ↗ | Unverified — from internal inventory | Compute from CSCL intersections; verify against signalized intersection list. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-06-21 | Not started
DS-032 | DPR | Parks Properties (polygons) | Out-of-scope mask | Shp / GeoJSON | Public | P2 | — | Quarterly | Mask park surfaces from the legal-vending canvas; vending in parks is out of scope. | open ↗ | Public source — link present in inventory | Surface as 'out of scope' rather than 'prohibited' in the UX. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-14 | Not started
DS-033 | DOE | School Point Locations | Buffer anchor | GeoJSON / CSV | Public | P2 | — | Annual | School-hours restrictions for food vendors; cross-reference with DOHMH list for explicit segment restrictions. | open ↗ | Public source — link present in inventory | Verify whether school-hours rules are encoded in the DOHMH list or applied separately. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-21 | Not started
DS-034 | MTA / NYS | Subway Entrances and Exits 2024 | Buffer anchor | GeoJSON / API (Socrata) | Public | P1 | D3 (subway buffers) | Annual | 10-ft subway entrance buffer; 5,000+ point features statewide. Critical density input. | open ↗ | Public source — link present in inventory | Confirm 2025/2026 release schedule with MTA Open Data. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-07 | Not started
DS-035 | MTA / NYS | MTA Bus Stops | Buffer anchor | GeoJSON / API | Public | P2 | — | Monthly | No-vending-at-bus-stops rule, broader than just sheltered stops. | open ↗ | Public source — link present in inventory | Union with DS-027 (sheltered) for complete coverage. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-14 | Not started
DS-036 | FDNY / DEP | Fire Hydrants | Buffer anchor | Shp / CSV | Public | P2 | — | Quarterly | Vending against hydrants is prohibited; anchor for ~15-ft buffer. | open ↗ | Public source — link present in inventory | Combine with DEP hydrant data for completeness. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-28 | Not started
DS-037 | FDNY / DEP | Sidewalk ventilation grates | Buffer anchor | — | Gap | P3 | — | — | §20-465(a) prohibits vending on ventilation grilles. No public citywide layer identified. |  | Unverified — from internal inventory | Likely uncovered in v1; document as known limitation. Possible OSM contribution path. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-07-19 | Not started
DS-038 | OTI / Open Data | 311 Service Requests (vendor-related) | Operational / measurement | CSV / API (Socrata) | Public | P2 | — | Daily | Pre/post complaint-volume measurement per §IV.4.a; filter complaint_type for vendor descriptors. | open ↗ | Public source — link present in inventory | Validate vendor-related complaint type values with SBS during Phase 1. ¦ Open Data / agency portal; not individually fetched this session. | Live XYZ — Data Lead | 2026-06-28 | Not started
DS-039 | OTI / Open Data | SAM (Streets and Address Matching) Address Points | Base geography | Shp / API | Public | P3 | — | Daily | Address-to-point geocoding for the address-search feature (§4.C bullet 3). | open ↗ | Unverified — from internal inventory | Compare with USPS / Google Geocoding fallback. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-07-12 | Not started
DS-040 | Community / OSM | Sidewalk Widths NYC | Base geography | GeoJSON | Public (OSM derivative) | P2 | — | Ad-hoc | Per-segment sidewalk widths — required to evaluate the 12-ft pedestrian-clearance rule. | open ↗ | Unverified — from internal inventory | Community-maintained. Replace with DS-030 if DOT releases an authoritative version. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-06-14 | Not started
DS-041 | DCP | Sidewalk polygons (DCP) | Base geography | Shp | Public | P2 | — | Annual | Authoritative sidewalk geometry; pairs with DS-040 widths and DS-013 CSCL. | open ↗ | Unverified — from internal inventory | Validate against DOT's inventory if DS-030 surfaces. ¦ URL carried from v1.0; not independently confirmed this session. | Live XYZ — Data Lead | 2026-06-14 | Not started

## Critical Path (P1)
Critical Path — P1 Datasets Blocking Rule Encoding (Deliverable #3)
These 8 datasets gate Phase 2 rule translation. None can begin until the contract is executed and SBS makes agency introductions (per E.D. Kaufman-Gutierrez, 2026-06-03 kickoff).
ID | Agency | Dataset | Why critical | Acquisition route | Target date | Verification (2026-06-03) | Status
DS-012 | DCP | NYC GIS Zoning Features | Drives the §20-465 C4/C5/C6 general-vendor zoning-district exclusion. Critical for SKU-specific legality. | Public | 2026-06-07 | Public source confirmed | Not started
DS-013 | DCP | NYC Street Centerline (CSCL) | Primary streets layer; segment IDs are the join key for DOHMH/DCWP street-level restrictions. | Public | 2026-06-07 | Public source confirmed | Not started
DS-034 | MTA / NYS | Subway Entrances and Exits 2024 | 10-ft subway entrance buffer; 5,000+ point features statewide. Critical density input. | Public | 2026-06-07 | Public source confirmed | Not started
DS-001 | DOHMH | Mobile Food Vending Restricted Streets — GIS layer | Canonical food-vendor no-go segments with hours/days. Single most important rule input. | Request to agency | 2026-06-21 | Public map confirmed; GIS layer NOT yet requested | Not started
DS-005 | DOHMH | Green Cart designated under-served neighborhood polygons | Green Cart MFV permits limited to specific Police Precinct geographies in lower-income areas. | Request to agency | 2026-06-21 | Unverified — internal inventory | Not started
DS-007 | DCWP | General Vendor Street Restrictions — Esri feature service | Authoritative DCWP-administered street restrictions for general (merchandise) vendors per §20-465 / §20-465.1. | Public via ArcGIS Experience; license preferred | 2026-06-21 | Verified live (2026-06-03) | Not started
DS-003 | DOHMH | Restricted Area Permit zones | Defines the specific high-traffic zones requiring Restricted Area Permit (separate SKU). | Request to agency | 2026-06-28 | Unverified — internal inventory | Not started
DS-023 | DSNY | ECB vendor citation records (geocoded) | Citation locations, code sections, dispositions. Underpins §IV.4.a evaluation and 75%-overturn root-cause analysis. | Request to agency / OpenRecords | 2026-06-28 | Unverified — internal inventory | Not started

## Status Dashboard
Status Dashboard
Live counts via formula. Update the Status column on Master Tracker; this recalculates.
By Status |  | By Priority
Status | Count | Priority | Count
Not started | 41 | P1 | 8
In progress | 0 | P2 | 23
Acquired | 0 | P3 | 10
Blocked | 0
TOTAL | 41
Verification status (2026-06-03)
Independently verified / public confirmed this session | 23
Unverified (carried from internal inventory) | 18

## Change Log
Change Log — what changed from inventory v1.0 → tracker v2.0
Date | Change | Detail
2026-06-03 | Restructured into official tracker | Added Blocks-deliverable, Verification, and Status-dashboard sheets so engineering/PM can audit.
2026-06-03 | Verified DS-007 = the public DCWP map | Confirmed the ArcGIS Experience URL is live and IS the official NYC General Vendor Street Restrictions Map. Reuse, do not rebuild.
2026-06-03 | Confirmed DOHMH public MFV map | Live at a816-dohbesp.nyc.gov/IndicatorPublic/mobilefoodvending. DS-001 GIS export still must be requested separately.
2026-06-03 | Flagged unverified links | All DS rows not independently confirmed this session are marked "Unverified — from internal inventory."
2026-06-03 | See Open Questions Log | WTC north-border (Vesey vs Barclay) and First-Amendment-follows-Blue conflicts logged for agency verification before encoding.