# Jason Notes

The key will be

what of the vendor profiles (food, etc) what types of permits tissue

What are all the rules relating to these permits?

Where do all these rules live (agencies)

What is the data we need in order to code these rules?

# Meeting Agenda

PRE-MEETING BRIEF & AGENDA

# Project Kickoff — Street Vendor Services Platform

| Date | Wednesday, June 10, 2026 |
| --- | --- |
| Attendees | Chris (you) & Carina Kaufman-Gutierrez, Executive Director, NYC Office of Street Vendor Services (SVS) |
| Purpose | Project kickoff — align on scope, deliverables, meeting cadence, interagency partners, and Carina's vision for the platform |
| Deliverable #1 | Meeting readout / action items log |

PART 1 — PRE-MEETING BRIEF

## Who Is Carina Kaufman-Gutierrez?

Carina was recently named the first-ever Executive Director of the newly created NYC Office of Street Vendor Services (SVS), housed within the Department of Small Business Services (SBS). This is a brand-new office created specifically to centralize support for street vendors navigating city systems.

Her background is deeply vendor-side:

- Nearly 7 years at the Street Vendor Project  —  a vendor advocacy organization — she knows the pain points firsthand

- Prior roles at SBS, GrowNYC Greenmarkets, and the Community Service Society

- Strong relationships across the vendor community and city agencies

## What Her Office Does

SVS is designed to be a one-stop shop for street vendors — helping them understand permits, licenses, enforcement rules, and how to navigate city bureaucracy. The office coordinates across multiple agencies that all touch the vendor experience.

## Why This Meeting Matters

Carina is the primary stakeholder and subject-matter expert for this platform. Her perspective will shape:

- What the product actually needs to do for vendors

- Which agencies are critical to involve

- What success looks like from the city's perspective

- The tone, language, and UX approach that will resonate with the vendor community

## Suggested Questions to Have Ready

For Agenda Item 4 (Vision & UX), consider coming prepared with:

- What do vendors ask SVS about most frequently?

- Where does the current system most commonly break down for them?

- Are there language or literacy barriers to consider in the UX?

- What does a "successful" interaction with this platform look like for a vendor?

- Are there any agencies or contacts you'd add to our outreach list beyond DCWP, DOHMH, DOT, and DPR?

- What tone or terminology resonates with vendors — and what doesn't?

## Context on the Deliverables

The project has three deliverables. Today's meeting primarily advances Deliverable #1:

- Deliverable #1 — Project Kickoff (due June 30, 2026) — Initiate project, review scope and alignment. Invoice doc required: Readout from kickoff meeting including action items.

- Deliverable #2 — Governance Alignment + Pilot Scope Finalized (due August 3, 2026) — Finalized Scope, Project Plan, and Street Vendor survey to benchmark metrics for success. Invoice docs: Finalized Scope, Business Requirements Document, Detailed Work Plan with milestones, street vendor survey and work plan, Summary of features and requirements.

- Deliverable #3 — Rule Library v1 + Prototype Platform Demo (due November 2, 2026) — Prototype converting text-based regulations into map-based logic (permitted/restricted/prohibited); vendor-facing map UX with plain-language explanations; rule library; multi-lingual support in 10 NYC languages + Wolof (Local Law 30); feedback tool; customer notification sign-up. Invoice docs: prototype demo/screenshots, agency rules mapping, data systems, regulation index, and translated rules.

PART 2 — MEETING AGENDA

Total estimated time: ~60 minutes

| # | Topic | Time |
| --- | --- | --- |
| 1 | Project Deliverables Overview Walk through Deliverables #1–3 at a high level, then focus on Deliverable #1 — confirming scope, alignment, and action items. The readout from today's meeting serves as the primary Deliverable #1 output. ★ Primary focus | ~20 min |
| 2 | Meeting Cadence with SBS Agree on a recurring meeting schedule — frequency, format, and key SBS stakeholders to include on a standing call. ◆ Logistics | ~10 min |
| 3 | Interagency Meeting Roster Identify key contacts and meeting owners across partner agencies: DCWP, DOHMH, DOT, DPR, and any others Carina recommends based on the enforcement and permitting landscape. ◆ Planning | ~10 min |
| 4 | Vision, Product Requirements & UX Priorities Hear Carina's perspective on the problems vendors face navigating city systems today, what success looks like for the platform, and early thoughts on user experience, tone, and must-have features. ★ Key discussion | ~20 min |

PART 3 — ACTION ITEMS (TO COMPLETE DURING MEETING)

| Action Item | Owner | Due Date |
| --- | --- | --- |

Notes

# Street Vendors Rules

STREET VENDOR SITE SELECTION TOOL

Where Can Vendors Legally Operate?

Live XYZ  x  NYC SBS  x  Street Vendor Project  |  June 2026  |  DRAFT

What this document is These rules come directly from NYC law — nothing here is made up. Our job is to turn these rules into a map that vendors can actually use.

Who this is for Project managers, outreach staff, and anyone on the team who needs to understand what the tool does — without having to read legal code. Engineers have a separate technical document with the full specifications.

# 1. The Big Picture

Right now, there is no single map that shows where a street vendor can legally operate in New York City. The rules exist — but they are spread across multiple city agencies, written in legal text, and nearly impossible for a vendor to translate into 'can I set up here?'

Our tool solves this by converting all those rules into a color-coded map:

GREEN — Permitted: You can vend here

YELLOW — Restricted: You can vend here, but only at certain times or with certain permits

RED — Prohibited: You cannot vend here

GRAY — Out of Scope: Parks and plazas (these use a separate permit system)

The rules fall into four categories, each covered in this document:

- Vendor types — different permits have different rights

- Sidewalk rules — how much space must be left for pedestrians

- Stay-away distances — how far from subway entrances, bus stops, driveways, etc.

- No-go zones — entire areas where vending is banned or restricted

# 2. The Two Types of Vendors

NYC has two completely separate legal systems for street vending, depending on what you sell. The map needs to handle both.

## Food Vendors (Mobile Food Vendors / MFV)

Sells food from a cart or truck. Regulated by the NYC Department of Health (DOHMH).

- Citywide Permit — can vend anywhere in all 5 boroughs, year-round

- Borough-Specific Permit — can only vend in one specific borough (not Manhattan)

- Green Cart Permit — can only sell fresh fruits, vegetables, water, and raw nuts. Limited to specific lower-income neighborhoods.

- Seasonal Permit — can only vend April 1 through October 31

Important for the map Important for the map A food vendor's permit type determines which boroughs they can operate in. The map must ask vendors which permit type they have before showing them where they can go.

## Merchandise Vendors (General Vendors / GV)

Sells non-food goods (clothing, accessories, art, etc.). Regulated by DCWP.

- Standard License — limited to 853 licenses citywide. Cannot operate in major commercial zones (see Section 5).

- Yellow Specialized License — for veterans with a service-related disability. Can operate in some areas where standard licenses cannot.

- Blue Midtown Core License — for disabled veterans only. Required to operate in the Midtown area. Only 105 exist.

Note on First Amendment vendors Note on First Amendment vendors People selling books, newspapers, artwork, or prints do not need a license. But they still must follow all the same placement and location rules as everyone else.

# 3. Sidewalk Rules (Apply to Everyone)

These rules apply to all vendors, regardless of permit type. They are about how much space a vendor can take up on the sidewalk.

| Rule 1 — Leave 12 feet clear for pedestrians |  |
| --- | --- |
| The rule A vendor must always leave at least 12 feet of clear walkway on the sidewalk, measured from the building wall to the nearest obstruction, or to the curb if there are none. Applies to: All vendors | What the team needs to do The map needs sidewalk width data for every block. If the total sidewalk is 12 feet or less, no vending is possible there. We're getting this data from a community dataset (DS-040) and DCP sidewalk polygons (DS-041). |

| Rule 2 — Set up at the curb, not near the building |  |
| --- | --- |
| The rule Carts and stands must be placed next to the curb — the street side of the sidewalk. You cannot set up near the building wall. Applies to: All vendors | What the team needs to do The tool must show this as a placement reminder whenever a vendor selects any location. It can't be enforced block-by-block on the map. |

| Rule 3 — Don't touch street furniture |  |
| --- | --- |
| The rule Nothing belonging to the vendor — cart, goods, umbrella, anything — can touch or lean against a lamppost, parking meter, mailbox, fire hydrant, tree box, bench, bus shelter, trash can, or traffic barrier. Applies to: All vendors | What the team needs to do This is an on-the-day operational rule. The tool must show it as a reminder at every location. |

| Rule 4 — No vending over grates or manholes |  |
| --- | --- |
| The rule Vendors cannot set up over any ventilation grill, cellar door, manhole, or subway grating. Applies to: All vendors | What the team needs to do We don't have map data for this. It will be a written reminder in the UX for v1, and flagged as a known gap. |

| Rule 5 — No vending in bike lanes or on medians |  |
| --- | --- |
| The rule Carts and goods cannot be placed in a bike lane. No vending on road medians (unless it's a designated pedestrian plaza). Applies to: All vendors | What the team needs to do NYC DOT bike lane data is publicly available and will be added as a prohibited layer on the map. |

# 4. Stay-Away Distances

Vendors must stay a minimum distance from specific features on the street. These create 'exclusion zones' that the map draws automatically around every relevant feature across the city.

| What to stay away from | How far | Who | Data needed |
| --- | --- | --- | --- |
| Subway entrance or exit | 10 ft | Both | MTA Subway Entrances (DS-034) — 5,000+ points citywide. CRITICAL — needed before map can be built. |
| Building entrance or exit | 20 ft | Both | Building Footprints (DS-015). Note: we're approximating from the building edge since we don't have exact door locations. |
| Driveway or curb cut | 10 ft | Both | NO CLEAN DATA EXISTS (DS-029). Known gap — we'll use a rough approximation for v1 and flag the limitation to vendors. |
| Crosswalk | 10 ft | Food vendors only | Calculated from street centerline data (DS-013/DS-031). |
| Street corner | 10 ft | Merch vendors only | Calculated from street centerline data (DS-013). |
| Sidewalk cafe or stoop stand | 20 ft | Both | No single public map exists. Must pull from DCWP licensed premises records. |
| Bus shelter | 5 ft | Merch vendors only | DOT Bus Stop Shelters (DS-027) + MTA Bus Stops (DS-035). |
| Newsstand | 5 ft | Merch vendors only | DCWP newsstand permits. |
| Disabled access ramp | 5 ft | Merch vendors only | ADA ramp / curb cut locations. |
| Bus stop or taxi stand | Entire area | Both | MTA Bus Stops (DS-035) + DOT Bus Shelters (DS-027). No vending within the marked stop boundary. |
| Hospital no-standing zone | Entire zone | Both | Hospital locations (DS-006/DS-017) combined with DOT no-standing sign data (DS-028). |

How this works technically How this works technically Each feature in the table above gets an invisible 'buffer zone' drawn around it on the map. The team needs to acquire the data in the right column to draw these buffers accurately. The subway entrance data (DS-034) is the top priority — there are over 5,000 subway entrances across the city.

# 5. No-Go Zones (Entire Areas)

Some entire geographic areas are completely off-limits for vending, or restricted to vendors with special licenses.

## 5a. Major Commercial Areas — Merchandise Vendors

PROHIBITED for standard licenses PROHIBITED for standard licenses Standard merchandise vendor licenses cannot be used in C4, C5, or C6 commercial zones. These cover major commercial corridors across all five boroughs. Only Yellow or Blue Specialized licenses (both reserved for veterans) are allowed here. This is one of the most important layers on the map for merchandise vendors — the zoning data (DS-012) is publicly available.

## 5b. Midtown Core Zone — Merchandise Vendors

PROHIBITED except for Blue license holders PROHIBITED except for Blue license holders The Midtown Core Zone (roughly 30th to 65th Street, Second Ave to Ninth/Columbus Ave) requires a Blue Specialized license to vend. There are only 105 Blue licenses in existence, all reserved for disabled veterans.

## 5c. World Trade Center Area — Both Vendor Types

PROHIBITED, with three specific street exceptions for food vendors PROHIBITED, with three specific street exceptions for food vendors Bounded by Broadway (east), Liberty Street (south), West Street (west), and Barclay Street (north). No vending allowed throughout the zone. Three streets are exceptions for food vendors only: Broadway between Barclay and Vesey; east side of West Street between Barclay and Vesey; south side of Barclay between Church and Broadway.

## 5d. Downtown Flushing, Queens — Merchandise Vendors

PROHIBITED for standard licenses PROHIBITED for standard licenses Bounded by Union Street (east), Sanford Ave (south), College Point Blvd (west), Northern Blvd (north). Standard General Vendor licenses are not valid here. Yellow or Blue license holders are exempt.

## 5e. Dyker Heights, Brooklyn — Merchandise Vendors (Holiday Season)

RESTRICTED during holiday season hours RESTRICTED during holiday season hours From Thanksgiving through New Year's Day, no standard merchandise vending allowed between midnight-6am or 2pm-midnight. Zone: 10th Ave to 13th Ave, 81st to 86th Street. Specialized license holders are exempt. This is the only time-based seasonal zone restriction.

## 5f. DOHMH Restricted Streets — Food Vendors

RESTRICTED — specific streets have time and day limits for food vending RESTRICTED — specific streets have time and day limits for food vending The NYC Health Department maintains a list of specific streets where food vending is restricted by time of day and/or day of week. This is the single most important dataset for food vendors. Example: a street might allow food vending only after 6pm on weekdays. We need the GIS version of this list from DOHMH (DS-001) by June 21. If we can't get it, manually converting the PDF adds ~2 weeks of extra work.

## 5g. Green Cart Zones

PERMITTED only in designated precincts PERMITTED only in designated precincts Green Cart permits are only valid in specific underserved neighborhoods, defined by police precinct boundaries. Each permit specifies exactly where the vendor can operate. We need the boundary polygons from DOHMH (DS-005) by June 21.

## 5h. Parks and Pedestrian Plazas — Out of Scope

OUT OF SCOPE — not covered by this tool OUT OF SCOPE — not covered by this tool Vending in NYC parks uses a completely separate permit system managed by the Parks Department. DOT pedestrian plazas are concession-only. The map shows these as 'out of scope' — not 'prohibited.' A vendor with a parks concession permit may be allowed there; our tool just doesn't cover that arrangement.

# 6. Data We Still Need

The map can only be as accurate as the data behind it. The table below lists the open issues the team needs to resolve.

| # | Issue | What it means for the project |
| --- | --- | --- |
| 1 [CRITICAL] | DOHMH Restricted Streets GIS (DS-001) | The most critical dataset for food vendors. We need the GIS file from DOHMH by June 21. Without it, encoding the restricted streets list takes ~2 extra weeks of manual work. |
| 2 [CRITICAL] | Green Cart precinct boundaries (DS-005) | Without this, we can't show Green Cart vendors where they're allowed to operate. Needed from DOHMH by June 21. |
| 3 [CRITICAL] | DCWP General Vendor street restrictions (DS-007) | The authoritative list of streets where merchandise vending is/isn't allowed. Publicly accessible but we need a written license agreement before using it in production. |
| 4 | Driveway and curb-cut locations (DS-029) | No clean citywide map exists. We'll use an approximation for v1, but it won't be 100% accurate. Vendors should be told this in the UX. |
| 5 | Sidewalk cafe locations | Vendors must stay 20 ft away, but there's no single public map. We'll need to pull this from DCWP licensing records. |
| 6 | Ventilation grates (DS-037) | No citywide map exists. Can't show this on the map in v1 — will include as a written reminder instead. |
| 7 | SVRP street designation history (DS-008/DS-020) | The Street Vendor Review Panel has been updating the permitted street list since 1995. We need to confirm with SBS whether the DCWP map already reflects all these changes. |

# 7. How the Map Decides What to Show

When a vendor looks up a location, the tool runs through this checklist in order — from most restrictive to least:

- Is it a park or plaza? Show as Out of Scope. Stop.

- Is it in a hard no-go zone? Show as Prohibited. Stop.

- Does the vendor's license allow them here? If not (e.g. standard merchandise license in a commercial zone), show as Prohibited for their license type.

- Are there time restrictions here? Show as Restricted with the applicable hours.

- Is the location within a stay-away buffer? Show as Prohibited.

- Is the sidewalk wide enough? If less than 12 ft, show as Prohibited.

- None of the above? Show as Permitted — with reminders about operational rules (stay at curb, don't block entrances, etc.).

# 8. A Note on Accuracy

These rules come directly from NYC law These rules come directly from NYC law Everything in this document is based on the actual NYC Administrative Code and guidance published by city agencies. We have not invented or assumed any rules. If a rule can't be confirmed from an official source, we've flagged it as a gap rather than guessing.

That said, this tool is a guide to help vendors make better decisions — not a legal guarantee. Rules can change, and some situations need human judgment. Vendors should be encouraged to check with 311 or the relevant agency if they're unsure about a specific location.

Legal sources behind this document:

- NYC Administrative Code §17-315 — food vendor placement rules (DOHMH)

- NYC Administrative Code §20-465 — merchandise vendor placement rules (DCWP)

- DOHMH Mobile Food Vendor Restricted Streets Guide (official agency publication)

- DSNY Educational Guides for Food and General Vendors (May 2023)

# Street Vendors - Engineer Team

STREET VENDOR SITE SELECTION TOOL

NYC Legal Location Rules

Engineering Requirements — Rule Translation Layer (Phase 2)

Live XYZ  ×  NYC SBS  ×  Street Vendor Project

Version 1.0  |  June 2026  |  DRAFT

⚠️ Important Note on Legal Accuracy All rules in this document are drawn directly from official NYC legal sources: NYC Administrative Code §17-315 (Mobile Food Vendors), NYC Administrative Code §20-465 (General Vendors), DOHMH and DCWP educational guidance published by DSNY (May 2023). These requirements must not be changed or reinterpreted without legal review. If a rule cannot be confirmed from a primary source, it must be flagged as unverified and excluded from the v1 map logic.

# 1. Purpose & Scope

This document specifies the legal placement and location rules that must be encoded into the Street Vendor Site Selection Tool map logic. It covers two vendor categories governed by separate legal frameworks:

- Mobile Food Vendors (MFV) — food carts and food trucks operating on NYC public streets and sidewalks, regulated by DOHMH under NYC Administrative Code §17-315.

- General Vendors (GV) — merchandise/goods vendors (non-food) operating on NYC public streets and sidewalks, regulated by DCWP under NYC Administrative Code §20-465.

The tool must translate these text-based rules into spatial geometry — producing a per-block-segment determination of: PERMITTED, RESTRICTED (with conditions/hours), or PROHIBITED — for each vendor type.

🚫 Out of Scope for v1 Parks (DPR jurisdiction), pedestrian plazas (DOT-designated), private property, and street fairs. These surfaces should be masked as 'out of scope' in the UX — not labeled 'prohibited.'

# 2. Vendor Type Definitions

The map must support filtering by vendor type, as rules differ significantly between them. The following SKU taxonomy must be implemented:

## 2.1 Mobile Food Vendors (MFV)

Governed by: NYC Administrative Code §17-315 and DOHMH rules (24 RCNY §6-04, §6-06)

- Citywide Full-Term Permit — Can vend year-round on public streets in all 5 boroughs. Subject to street-specific restrictions from the DOHMH Restricted Streets list.

- Borough-Specific Permit (excl. Manhattan) — Can vend year-round in Bronx, Brooklyn, Queens, or Staten Island only. Cannot operate in Manhattan.

- Green Cart Permit (Fruit & Vegetable) — Can only sell whole fresh fruits, vegetables, water, and raw single-ingredient nuts. Must operate in their designated police precinct geography in underserved neighborhoods.

- Seasonal Permit — Valid April 1 through October 31 only. Citywide.

- Specialized / Restricted Area Permit — For operation on private property or DPR-managed parks. Cannot vend in public areas. Out of scope for this tool.

📋 Source: NYC Admin Code §17-307(b)(1) — DOHMH Mobile Food Vendor Licensing Law (DSNY Educational Guide, May 2023)

## 2.2 General Vendors (GV)

Governed by: NYC Administrative Code §20-465 and DCWP rules (6 RCNY 2-314)

- Standard General Vendor License — Non-veteran license. Cap of 853 licenses citywide. Cannot vend in C4/C5/C6 zoning districts or in the Midtown Core area without a Specialized license.

- Citywide Specialized (Yellow) — Reserved for veterans with service-related disability. No license cap. Can vend in certain restricted areas where standard GV licenses cannot.

- Midtown Core Zone (Blue) — Reserved for disabled veterans/survivors. Limited to 105 licenses. Required to vend within the Midtown Core zone boundary.

Note: First Amendment vendors (books, newspapers, artwork, paintings, photographs, prints, sculptures) do not require a General Vendor license but must still comply with all placement and location rules under §20-465.

📋 Source: NYC Admin Code §20-453, §20-465 — DCWP General Vendor Licensing Law (DSNY Educational Guide, May 2023)

# 3. Universal Placement Rules (Both Vendor Types)

The following rules apply to both MFV and GV unless otherwise noted. They must be enforced as hard constraints in the map logic regardless of permit type.

## 3.1 Minimum Sidewalk Clearance

RULE: Must leave at least 12 feet of clear pedestrian path on the sidewalk at all times.

- Measurement method: Measured from the boundary of private property (building line) to any obstruction on the sidewalk. If there are no obstructions, measured to the curb.

- Placement constraint: The pushcart or stand must be placed only in the portion of the sidewalk that abuts the curb. It may not be placed in the building-line portion of the sidewalk.

- Engineering implication: This rule requires sidewalk width data per block segment. Segments where the total sidewalk width is ≤12 feet must be flagged PROHIBITED. Segments where width is between 12–15 feet should be flagged RESTRICTED with a UX warning. Datasource: DS-040 (Sidewalk Widths NYC) and DS-041 (DCP Sidewalk polygons).

📋 Source: NYC Admin Code §17-315(a) / §20-465(a) — Mobile Food Vendor and General Vendor Placement Rules

## 3.2 Curb Placement — Pushcarts Must Be at the Curb

RULE: Pushcarts and stands must be placed next to the curb only. No placement on the building-line half of the sidewalk.

- Engineering implication: The map must show that only the curb-adjacent portion of a sidewalk is valid for placement. This is a positional rule, not a buffer, and should be communicated in UX as 'must set up next to the curb.'

📋 Source: NYC Admin Code §17-315(a) / §20-465(a) — Placement next to curb only

## 3.3 No Contact with Street Furniture or Structures

RULE: No part of the vending unit, goods, or equipment may touch or be affixed to any building or street structure.

Prohibited structures include but are not limited to:

- Lamp posts, parking meters, mail boxes

- Traffic signal stanchions, fire hydrants

- Tree boxes, benches, bus shelters

- Refuse baskets, traffic barriers

This is an operational rule. It cannot be spatially pre-encoded per-segment (contact is a real-time condition), but the UX must surface it as a rule reminder when a vendor selects any location.

📋 Source: NYC Admin Code §17-315(b) / §20-465(c) — No attachment to structures

## 3.4 No Vending on Ventilation Grates or Underground Infrastructure

RULE: No vending over any ventilation grill, cellar door, manhole, transformer vault, or subway access grating.

Engineering note: No authoritative citywide GIS layer for ventilation grates has been identified (see DS-037, flagged as a gap). This rule cannot be spatially encoded in v1. Document as a known limitation in the UX.

📋 Source: NYC Admin Code §20-465(m) — General Vendor — ventilation grates. Also applies to MFV operationally.

## 3.5 No Vending in Bicycle Lanes

RULE: No vending vehicle, pushcart, stand, or goods may be placed within a bicycle lane.

Engineering note: NYC DOT bicycle lane GIS data is publicly available. Bicycle lanes must be masked as PROHIBITED in the map layer.

📋 Source: NYC Admin Code §17-315(g) / §20-465(h) — No vending in bicycle lanes

## 3.6 No Vending on Median Strips

RULE: No vending on the median strip of a divided roadway, unless the strip is designated as a pedestrian mall or plaza.

📋 Source: NYC Admin Code §17-315(h) / §20-465(i) — No vending on medians

# 4. Distance Buffer Rules

The following rules create spatial exclusion zones (buffers) around specific point or line features. These must be computed as geometric buffers applied to the base street centerline and sidewalk layers.

🔧 Engineering Note — Buffer Implementation Buffers must be computed from the relevant anchor feature (subway entrance point, crosswalk edge, building entrance, etc.) and applied to the CSCL street segments (DS-013). Results must be stored as pre-computed prohibition polygons on the rule layer, not computed at query time.

## 4.1 Buffer Rules Summary Table

| Rule / Restriction | Vendor Type | Distance | Legal Source | Engineering Notes |
| --- | --- | --- | --- | --- |
| Subway entrance / exit | Both | 10 ft | §17-315(e) / §20-465(e) | Buffer from entrance/exit point. DS-034 (MTA Subway Entrances). |
| Crosswalk at intersection | MFV | 10 ft | §17-315(e) | MFV only. Buffer from crosswalk edge. Derived from CSCL intersection nodes (DS-031). |
| Corner / intersection | GV | 10 ft | §20-465(e) | GV only. Measured from point where property line of nearest block face meets curb. |
| Driveway / curb cut | Both | 10 ft | §17-315(e) / §20-465(e) | No authoritative citywide layer. DS-029 flagged as gap. Use building footprint / OSM derivation for v1. |
| Building entrance / exit | Both | 20 ft | §17-315(d) / §20-465(d) | MFV: 20 ft from entrance/exit of any building. GV: 20 ft from any entranceway to store, theatre, sports arena, place of public assembly, or residential building service exits. |
| Sidewalk café / stoop line stand | Both | 20 ft | §17-315(d) / §20-465(q) | Buffer from licensed sidewalk café or stoop line stand boundary. No single authoritative GIS layer — derive from DCWP licensed premises data. |
| Bus shelter | GV | 5 ft | §20-465(q) | GV only. DS-027 (DOT Bus Stop Shelters). |
| Newsstand | GV | 5 ft | §20-465(q) | GV only. Use DCWP newsstand permits. |
| Disabled access ramp | GV | 5 ft | §20-465(q) | GV only. Curb cut / ADA ramp locations. |
| Hospital — no-standing zone abutment | Both | No-standing zone | §17-315(e) / §20-465(e) | No vending on sidewalk abutting a no-standing zone adjacent to a hospital. DS-006 (hospitals), DS-028 (DOT no-standing signs). |
| Bus stop / taxi stand | Both | Within stop | §17-315(e) / §20-465(e) | No vending within any bus stop or taxi stand boundary. DS-027 + DS-035 (MTA Bus Stops). |
| Metered parking spot | MFV (roadway) | Not permitted | 34 RCNY §4-08(h)(7) | MFV only. Cannot operate from a metered parking space when vending in the roadway. |

📋 Source: Sources — NYC Admin Code §17-315(d)(e) / §20-465(d)(e)(q) / 34 RCNY §4-08(h)(7)

# 5. Zone-Based Prohibitions & Special Areas

These are geographic area rules that prohibit or restrict vending entirely within defined boundaries, regardless of sidewalk width or buffer clearance. They must be implemented as polygon masks on the map layer.

## 5.1 Zoning District Exclusion — General Vendors

RULE (GV only): No general vendor may vend on any street within a C4, C5, or C6 commercial zoning district — UNLESS they hold a Specialized (Yellow or Blue) license.

- Exception: Holders of Citywide Specialized (Yellow) or Midtown Core (Blue) licenses are exempt from this exclusion. These SKUs must be filterable in the map.

- Data source: DS-012 — NYC GIS Zoning Features (DCP). Filter ZONEDIST starting with C4, C5, C6. Dissolve to single exclusion polygon.

- Engineering note: This is one of the most important spatial rules for general vendors. C4/C5/C6 zones cover significant portions of Manhattan and major commercial corridors citywide.

📋 Source: NYC Admin Code §20-465(g)(1) — C4/C5/C6 zoning exclusion for general vendors

## 5.2 Midtown Core Zone — General Vendors

RULE (GV only): No general vendor may vend within the Midtown Core area UNLESS they hold a Blue (Midtown Core Zone) Specialized license.

Midtown Core boundary (§20-465(g)(1)):

- East: Second Avenue

- South: 30th Street

- West: Ninth Avenue and Columbus Avenue

- North: 65th Street

- Blue license required: Only Midtown Core Zone (Blue) Specialized licensees — reserved for disabled veterans and their surviving spouses — may vend within this boundary.

- Yellow license: Citywide Specialized (Yellow) license holders may vend in C4/C5/C6 zones citywide but the Midtown Core Zone specifically requires a Blue license.

📋 Source: NYC Admin Code §20-465(g)(1) — Midtown Core zone restriction

## 5.3 World Trade Center / Downtown Manhattan Zone

RULE (Both): No vending within the WTC Zone boundary. Limited exceptions apply for MFV on specific named streets.

WTC Zone boundary (both MFV and GV):

- East: eastern side of Broadway

- South: south side of Liberty Street

- West: west side of West Street

- North: south side of Barclay Street

MFV exceptions — vending permitted on:

- Broadway between Barclay Street and Vesey Street

- East side of West Street between Barclay Street and Vesey Street

- South side of Barclay Street between Church Street and Broadway

Additional absolute MFV prohibitions within and near WTC zone (no exceptions):

- Greenwich Street between Liberty Street and Thames Street

- East side of West Broadway between Barclay Street and Park Place

- Liberty Street between Trinity Place and West Street

- East side of West Street between Liberty Street and Cedar Street

- West side of Trinity Place between Liberty Street and Thames Street

GV version of WTC zone prohibition mirrors the same boundary, with the same three street-level exceptions for Broadway, West Street, and Barclay Street.

📋 Source: NYC Admin Code §17-315(k)(1) / §20-465(g)(2) — WTC zone restrictions for MFV and GV

## 5.4 Downtown Flushing, Queens — General Vendors

RULE (GV only): No general vendor may vend within the Flushing exclusion zone, unless they hold a Specialized (Yellow or Blue) license.

Flushing zone boundary (§20-465(g)(4)):

- East: eastern side of Union Street

- South: southern side of Sanford Avenue

- West: western side of College Point Boulevard

- North: northern side of Northern Boulevard

📋 Source: NYC Admin Code §20-465(g)(4) — Flushing exclusion zone

## 5.5 Dyker Heights, Brooklyn — General Vendors (Seasonal)

RULE (GV only): No general vendor may vend within the Dyker Heights zone from Thanksgiving through New Year's Day, during restricted hours — unless they hold a Specialized license.

Dyker Heights zone boundary (§20-465(g)(5)):

- West: western side of 10th Avenue

- South: southern side of 86th Street

- East: eastern side of 13th Avenue

- North: northern side of 81st Street

Restricted hours during the Thanksgiving–New Year's period:

- Midnight to 6:00 a.m.

- 2:00 p.m. to midnight

Engineering note: This is a time-based seasonal rule. The map must implement date-range and time-of-day logic for this segment. The restriction is in Brooklyn only.

📋 Source: NYC Admin Code §20-465(g)(5) — Dyker Heights seasonal restriction

## 5.6 DOHMH Restricted Streets List — Mobile Food Vendors

RULE (MFV only): DOHMH maintains a named list of streets with time/day-based MFV restrictions. These are block-level rules and are the single most important data source for MFV legality.

The Restricted Streets Guide (DOHMH, EHS334503E - 4.23) contains borough-by-borough tables with:

- Borough, street name, cross-street range (from / to)

- Time of year (year-round or seasonal)

- Day-by-day time restrictions (Sunday through Saturday, with start/end hours)

- Relevant code section (Admin Code 17-315 or RCNY 2-314)

Examples from the guide:

- West 53rd Street (Manhattan) between Broadway and Eighth Avenue: restricted 12pm–11pm on weekdays/weekends, year-round

- East 54th Street between Third Ave and Lexington Ave: restricted 7am–7pm all days, year-round

- Engineering priority: This is dataset DS-001 (P1 — blocking). The GIS layer from DOHMH is the canonical source. If the GIS layer cannot be obtained, the PDF guide must be geocoded against CSCL (DS-002, P2 fallback — approximately 2 engineering weeks).

- Engineering requirement: Each restricted street segment must store: permitted_start_time, permitted_end_time, restricted_days (bitmask or array), year_round (boolean), seasonal_start, seasonal_end.

📋 Source: DOHMH Restricted Streets Guide EHS334503E-4.23 / NYC Admin Code §17-315(k)(l) — MFV Restricted Streets List

# 6. Footprint & Size Rules

These rules govern the physical footprint a vendor may occupy. They are operational/UX rules and cannot be spatially pre-encoded per-segment, but must be surfaced in the tool UI when a vendor selects any location.

## 6.1 General Vendor Footprint Limits

- Maximum footprint parallel to curb: 8 linear feet

- Maximum depth from curb toward property line: 3 linear feet

- Maximum display height: 5 feet from ground level (umbrella may exceed this)

- Display surface: Must use a table, rack, or stand. Goods may not be placed directly on the sidewalk, on a blanket, board, cardboard, or trash receptacle.

- Storage: Only the space immediately below the display surface may be used for storage of items for sale.

- Electricity: General vendors may NOT use electricity, electrical generating equipment, or oil/gasoline-powered equipment of any kind.

📋 Source: NYC Admin Code §20-465(a)(b)(n)(p) — GV footprint and display rules

## 6.2 Mobile Food Vendor Footprint Rules

- Alignment: The longest side of the pushcart must be parallel to and next to the curb.

- Storage: Only the space immediately below the pushcart or vehicle may be used for storage.

- Food protection: Must have a covering (e.g., retractable umbrella) above the pushcart to protect food and equipment from contamination.

- Roadway vending: If vending from a parking space in the roadway (not sidewalk), must comply with all traffic and parking laws and may not block vehicular traffic. Cannot use a metered parking spot.

📋 Source: NYC Admin Code §17-315(a)(c) / 24 RCNY §6-04(o) / 24 RCNY §6-06(a) / 34 RCNY §4-08(h)(7) — MFV footprint rules

# 7. Parks & Out-of-Scope Surfaces

🔵 UX Guidance — 'Out of Scope' vs 'Prohibited' Parks, DOT pedestrian plazas, and concession areas are not governed by §17-315 or §20-465 — they have entirely separate licensing regimes managed by DPR and DOT. These surfaces must be masked as 'Out of Scope' in the tool UX, not labeled as 'Prohibited.' The distinction matters: a vendor with a Parks concession permit or Restricted Area Permit may be authorized to operate there, and the tool should not mislead them.

- Parks (DPR jurisdiction): No MFV or GV may vend within DPR-managed park areas without written authorization from the DPR Commissioner. Mask as out of scope. Data source: DS-032 (DPR Parks Properties polygons).

- Pedestrian Plazas (DOT): DOT-designated plaza surfaces are concession-only. Mask as out of scope. Data source: DS-026 (DOT Pedestrian Plazas).

- Median strips: No vending unless designated as pedestrian mall/plaza. Mask as out of scope / prohibited.

📋 Source: NYC Admin Code §17-315(i) / §20-465(j) — Parks jurisdiction exclusion

# 8. Green Cart — Specific Geographic Rules

Green Cart permits are a specialized MFV permit type with additional geographic constraints on top of standard MFV rules.

- Authorized geography: Green Cart holders may only operate in specific police precinct areas designated as underserved neighborhoods, established under Local Law 9 of 2008.

- Products: Limited to whole fresh fruits, vegetables, water, and raw single-ingredient nuts only.

- Borough: Green Cart permits are borough-specific. The permit decal specifies the authorized borough and police precinct.

- Engineering requirement: The map must support a Green Cart mode that overlays the authorized precinct boundaries. Data source: DS-005 (DOHMH Green Cart neighborhood polygons — P1). These boundaries are tied to police precinct geographies and may need conversion from a precinct list to GIS polygons.

📋 Source: NYC Admin Code §17-307(b)(1)(c) / Local Law 9 of 2008 — Green Cart geographic restrictions

# 9. Dataset–Rule Mapping (from Jason's Inventory)

The following datasets from the Phase 1 acquisition tracker (Data_Sets_.xlsx) directly correspond to the rules in this document. P1 datasets are blocking — Phase 2 rule encoding cannot proceed without them.

| ID | Dataset | Agency | Priority | Engineering use |
| --- | --- | --- | --- | --- |
| DS-001 | MFV Restricted Streets — GIS layer | DOHMH | P1 | Section 5.6 — MFV restricted street segments with hours/days |
| DS-002 | MFV Restricted Streets Guide (PDF fallback) | DOHMH | P2 | Fallback for DS-001 if GIS not provided; geocode against CSCL |
| DS-003 | Restricted Area Permit zones | DOHMH | P1 | High-traffic zones requiring Restricted Area Permit (separate SKU) |
| DS-005 | Green Cart designated polygons | DOHMH | P1 | Section 8 — Green Cart authorized precinct geographies |
| DS-007 | GV Street Restrictions — Esri feature service | DCWP | P1 | Section 5.1–5.2 — General vendor prohibited streets |
| DS-012 | NYC GIS Zoning Features | DCP | P1 | Section 5.1 — C4/C5/C6 exclusion zones for GV |
| DS-013 | NYC Street Centerline (CSCL) | DCP | P1 | Base layer — all rule buffers and restrictions join to CSCL segment IDs |
| DS-014 | LION Street Network | DCP | P2 | Partial-block resolution where restrictions describe 'from X to Y' |
| DS-015 | Building Footprints | DCP | P2 | Section 4.1 — 20 ft building entrance buffer (approximation) |
| DS-026 | Pedestrian Plazas (polygon) | DOT | P2 | Section 7 — mask plaza surfaces as out of scope |
| DS-027 | Bus Stop Shelters | DOT | P2 | Section 4.1 — 5 ft GV buffer from bus shelters |
| DS-029 | Curb-cut / Driveway inventory | DOT | P2 | Section 4.1 — 10 ft driveway buffer. FLAGGED AS GAP — no clean public layer. |
| DS-031 | Crosswalks (derived from CSCL) | DOT | P2 | Section 4.1 — 10 ft MFV crosswalk buffer |
| DS-032 | Parks Properties (polygon) | DPR | P2 | Section 7 — mask parks as out of scope |
| DS-034 | Subway Entrances and Exits | MTA/NYS | P1 | Section 4.1 — 10 ft buffer from subway entrances/exits (both vendor types) |
| DS-035 | MTA Bus Stops | MTA/NYS | P2 | Section 4.1 — no vending within bus stop boundaries |
| DS-040 | Sidewalk Widths NYC | Community/OSM | P2 | Section 3.1 — 12 ft pedestrian clearance rule; flag segments too narrow |
| DS-037 | Sidewalk ventilation grates | FDNY/DEP | P3 | Section 3.4 — KNOWN GAP, no public layer. Document as v1 limitation. |

# 10. Rule Conflict & Precedence Logic

When multiple rules apply to the same block segment simultaneously, the following precedence order must be applied by the rule engine:

- Out-of-scope mask (parks, plazas) — surface as 'out of scope,' do not evaluate further.

- Hard prohibition zones (WTC zone absolute streets, §17-315(k)(1) no-exception blocks) — surface as PROHIBITED.

- Zone exclusions by SKU (C4/C5/C6, Midtown Core, Flushing, WTC zone with exceptions) — surface as PROHIBITED for standard license; surface as PERMITTED or RESTRICTED for specialized license holders.

- Time-based / hour-based restrictions (DOHMH Restricted Streets list, Dyker Heights seasonal) — surface as RESTRICTED with applicable hours.

- Distance buffers (subway, crosswalk, driveway, building entrance, bus shelter) — surface as PROHIBITED at the buffered segment.

- Sidewalk width check — if remaining clear path after vendor placement < 12 ft, surface as PROHIBITED or RESTRICTED-WARNING.

- If no prohibition applies, surface as PERMITTED — with applicable operational reminders (entrance clearance, no touching structures, etc.).

# 11. Open Questions & Known Gaps

- GAP-001 — Driveway/Curb-cut GIS layer (DS-029): No authoritative citywide layer identified. Current plan: OSM/building-footprint derivation. Needs engineering sizing for v1 accuracy implications.

- GAP-002 — Ventilation grates (DS-037): No public citywide layer. Rule §20-465(m) cannot be spatially encoded in v1. Must be disclosed as known limitation in vendor-facing UX.

- GAP-003 — Sidewalk café / stoop line stand locations: DCWP issues licenses for these but no single public GIS layer has been confirmed. Needed for 20 ft buffer rule (§17-315(d) and §20-465(q)).

- GAP-004 — DOHMH GIS layer acquisition (DS-001): The Restricted Streets GIS layer is internal to DOHMH. Formal agency request required by June 21. If not obtained, fallback to PDF geocoding adds ~2 engineering weeks.

- GAP-005 — Partial-block DOHMH restrictions: Some DOHMH restrictions describe 'from X to Y' partial blocks (e.g., 'Broadway between Barclay and Vesey'). These require LION (DS-014) for accurate sub-segment encoding, not just CSCL.

- GAP-006 — NYS GBL §32 / §35-a veteran rules: State law contains additional restrictions specific to specialized vending licensees (veteran-specific blocks in Manhattan). These need legal review to confirm whether they are encoded in DS-007 or need separate treatment.

- GAP-007 — SVRP-designated streets (DS-008 / DS-020): The Street Vendor Review Panel has added/removed streets from the permitted set since 1995. These designations may not all be reflected in the DCWP ArcGIS feature service. SBS legal needs to confirm canonical source.

# 12. Legal Disclaimer

⚖️ For Engineering Planning Purposes Only This document is a working engineering requirements draft. It is based on officially published NYC Administrative Code provisions (§17-315, §20-465), DOHMH and DCWP educational materials published by DSNY (May 2023), and the NYC Restricted Streets Guide (DOHMH, EHS334503E-4.23). It is not exhaustive and does not constitute legal advice. All rules must be verified against the current NYC Administrative Code before production deployment. Rules are subject to amendment. Live XYZ and SBS are responsible for ensuring all encoded regulations reflect the authoritative and current legal text at time of launch.

Primary legal sources referenced in this document:

- NYC Administrative Code §17-315 — Restrictions on placement of vehicles and pushcarts; food vendors

- NYC Administrative Code §20-465 — Restrictions on placement of vehicles, pushcarts and stands; general vendors

- NYC Administrative Code §17-307(b)(1) — Mobile Food Vendor permit types

- NYC Administrative Code §20-453 — General vendor license

- 24 RCNY §6-04, §6-06 — DOHMH rules for mobile food vending units

- 6 RCNY 2-314 — DCWP rules for general vendors

- 34 RCNY §4-08(h)(7) — DOT rules (metered parking)

- DOHMH Mobile Food Vendor Restricted Streets Guide (EHS334503E-4.23)

- DSNY Educational Guides: Mobile Food Vendor Licensing Law (May 2023) / General Vendor Licensing Law (May 2023)

# Contract deliverables

Deliverable #1 — Project Kickoff

Due June 30, 2026

- Readout from kickoff meeting including action items

Deliverable #2 — Governance Alignment + Pilot Scope Finalized

Due August 3, 2026

- Finalized Scope

- Business Requirements Document

- Detailed Work Plan with milestones and delivery dates

- Street vendor survey to benchmark metrics and work plan to administer surveys

- Summary of features and requirements

Deliverable #3 — Rule Library v1 + Prototype Platform Demo

Due November 2, 2026

- Prototype of application (demo, screenshots, etc.)

- Mapping: agency rules and regulations, data system, regulation index

- Convert text-based regulations into map-based logic (permitted / restricted / prohibited)

- Vendor-facing map UX with plain-language explanations

- Rule library and update workflow established

- Multilingual support in 10 citywide languages (per NYC Local Law 30, 2017) and Wolof

- Feedback tool for reporting issues

- Ability for vendors to sign up for City agency notifications

- Translations of rules and regulations for review

Deliverable #4 — Beta Release + Iteration

Due January 8, 2027

- Beta version of application

- User Application Testing report

- Plan for next iterations

- Readout from SBS-led listening sessions and usability testing across vendor populations

Deliverable #5 — Pilot Launch + Reporting Package

Due March 1, 2027

- Application ready for distribution

- Training materials for outreach

- Launch and demo plan for agencies

- Multilingual vendor trainings co-hosted with SBS (10 citywide languages + Wolof)

- Enforcement agency trainings co-hosted with SBS

- Metrics dashboard tracking downloads, sharing, visits to online materials and assessments